## Checklist

It helps to set internal deadlines to ensure that important things get done in time. Consider completing a checklist for each event you host.

| Global Money Week 2015 Preparation Checklist |  |  |
| --- | --- | --- |
| Suggested Deadline | Task | Done? |
| Before the end of 2014 | Request a Toolkit from CYFI Additional copies and other materials can be requested from info@childfinance.org |  |
| Early January 3 months before Global Money Week Planning | Form planning team |  |
|  | Establish roles within planning team |  |
|  | Research and brainstorm different events to be held |  |
|  | Decide on events to be hosted |  |
|  | Determine how structure of event can contribute to values of Global Money Week |  |
|  | Planning Goals for Early January Completed: |  |
| Mid-January, 2015 10 weeks before Global Money Week Logistics | Choose date for event |  |
|  | Set budget for the event |  |
|  | Secure startup capital |  |
|  | Devise pay back plan for startup capital |  |
|  | Secure transportation to event |  |
|  | Secure equipment used for event |  |
|  | Request materials & equipment that may be loaned or donated |  |
|  | Delegate roles for volunteers |  |
|  | Input event dates on calendar |  |
|  | Draft schedule of events |  |
|  | Logistics Goals for Mid- January Completed: |  |
| Mid-January, 2015 10 weeks before Global Money Week Contact | Financial institution to visit |  |
|  | Potential corporate partners for the event |  |
|  | Media |  |
|  | Volunteers |  |
|  | Supervisors (if necessary) |  |
|  | Contact Goals for Mid-January Completed: |  |
| Mid-January, 2015 10 weeks before Global Money Week Promotion -------------------------------- | Print resources and post in conspicuous places |  |
|  | Share Global Money Week images on social media platforms |  |
|  | Print Pledge Sheet (GMW Print Pack)and share |  |
|  | Secure use of cameras and video cameras to document event |  |
|  | Post and promote event on social media platforms |  |
|  | Promotion Goals for Mid-January Completed: |  |
| March 9th -17th , 2015 One Week before Global Money Week Final Details | Hold meeting to finalize all logistics |  |
|  | Confirm schedule for day and distribute schedules |  |
|  | Final Detail Goals for March 9h-17th Completed: |  |
| Web conference |  |  |
| As soon as possible | Enter available times on online calendar |  |
| 1 week before scheduled date | Schedule test call |  |
| During Global Money Week 2015 | Host call |  |
|  | Webinar Goals Completed: |  |
| End of March, 2015 As soon as possible after Global Money Week Wrapping Up | Thank individuals and groups that helped make event possible |  |
|  | Complete and submit feedback form (found on 34) |  |
|  | Submit Global Money Week Champion Award Application before the deadline |  |
|  | Submit Global Money Week Country Award Application before the deadline. |  |
|  | Ensure your feedback is sent to CYFI secretariat |  |
|  | Submit pledge sheet to CYFI secretariat |  |
|  | Wrapping Up Goals Completed: |  |
| Mark your calendars for next year’s Global Money Week on March 9th -17th , 2015! |  |  |